Top Hat and Tails May 2010

Revenue

Petco Sponsor								$10,000

Purina Food Sponsor							$5,000

Donations								$3,575

150 Guests @ $180 ea.						$27,000

Silent/Live Auction							$4,500

TOTAL								$90,575

Expenses

Printing:

Invitations							$675

Save the Date Mailing						$450

Programs							$400

Postage							$600

150 Dinner Guests @$65 ea.						$9,750

DJ									$500

Photographer								$450

Decorations								$420

Gift Bags								$650

TOTAL								$13,895

GRAND TOTAL:							$76,680

Top Hat and Tails May 2010

January

Draft budget

Update sponsorship/invitation lists

Confirm date with Hotel

Sign contract

February

Solicit sponsorships

Prepare and mail Save the Date-Registration

Design invitations and flyers

Auction Committee Meeting

March

Prepare invitation

Finalize invitation

Continue to solicit sponsors

Investigate order premiums and giveaways

April

Mail invitations

Solicit volunteers

Purchase giveaways

Prepare Speakers and presentations

Prepare Live Auction

May

Confirm all details with Hotel

Confirm photographer

Confirm DJ

Design program for the day

Prepare check list for day of

Confirm # of people attending

Set up all decorations the morning of event

June

Prepare and send thank you/receipt letters

Follow up on outstanding payments